## Sheet1
| Project Number | Completed Y/N? | Entity | Project Description | Cost Remaining | Accrual Total (Feb 2023) | Cost Less Accrual | Project Manager | Date of Completion or Last PM Check | Responsible Accountant
236 | PRJ-2022-004175 |  | MAR | Alta Vista - 2022 - Care Floor Renovation | 123157.57 | 9908.86 | 113248.71 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
299 | PRJ-2022-004176 |  | MAR | Alta Vista - 2022 - Public Space Renovation | 100482.63 | 47851.77 | 52630.86 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
171 |  |  | MAR | Barrhaven - 2021 - 2nd Floor Renovation | -99868.41 | 0 | -99868.41 | Cameron Scully |  | Darrel
238 | PRJ-2022-004177 |  | MAR | Forest Hill - 2022 - Public Space Renovation | 210441.03 | 5236.7 | 205204.33 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
282 | PRJ-2022-004178 |  | MAR | Forest Hill - 2022 - Special Project | 12172.75 | 6325 | 5847.75 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
239 | PRJ-2022-004180 |  | MAR | Leaside - 2022 - Special Project | 284499.2 | 22020.9 | 262478.3 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
180 | PRJ-2021-001613 |  | MAR | The Kingsway - 2021 - Public Space Renovation | 2966424.99 | 0 | 2966424.99 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
208 | PRJ-2021-001613 |  | MAR | The Kingsway - Multi Yr - Public Space Renovation | 2385035.9 | 1916.66 | 2383119.24 | Cameron Scully | Not complete as of 11/22/2022 | Darrel
260 | PRJ-2022-004181 |  | MAR | The Westwood - 2022 - Public Space Renovation | 166735.34 | 15923.55 | 150811.79 | Cameron Scully | Not complete as of 11/22/2022 | Darrel