## Sheet1
| Project Number: | Date of Completion or Last PM Check | Balance | Completed? (Y/N) | PM | Accountant
32 | 92388719 | Cancelled - Dispose in Dec |  |  | Kerrsten Norwood | Nicole
34 | 92389701 | Consulting complete in Dec, work to commence in 2022 |  |  | Kerrsten Norwood | Nicole
31 | 94077707 | Not complete as of Dec 2021 |  |  | Kerrsten Norwood | Nicole
45 | Barrhaven - 2021 - 2nd Floor Renovation | Consulting complete in Dec, work to commence in 2022 | 544292.77 |  | Kerrsten Norwood | Nicole
52 | Barrhaven - 2021 - FAP & Devices | Consulting complete in Dec, work to commence in 2022 | 20905 |  | Kerrsten Norwood | Nicole
35 | Barrhaven Fire Door | Consulting complete in Dec, work to commence in 2022 | 13899 |  | Kerrsten Norwood | Nicole
66 | Carlingview - 2021 - Q2/Q4 Minor Capital Fund C | Not complete as of Dec 2021 | 7571 |  | Kerrsten Norwood | Nicole
65 | Carlingview Manor - Q2/Q4 - IPAC Capital Fund | N/A - IPAC | 123279 |  | Kerrsten Norwood | Nicole
39 | Colonel By - 2021 - 2nd Floor Reno | Consulting complete in Dec, work to commence in 2022 | 579865.2 |  | Kerrsten Norwood | Nicole
36 | Colonel By Memory Care Washroom | Consulting complete in Dec, work to commence in 2022 | 1832.86 |  | Kerrsten Norwood | Nicole
57 | Lynwood - 2021 - Building Refresh | Consulting complete in Dec, work to commence in 2022 | 30546.76 |  | Kerrsten Norwood | Nicole
37 | Lynwood Fire Doors | Consulting complete in Dec, work to commence in 2022 | 25990 |  | Kerrsten Norwood | Nicole
38 | Lynwood Public Washroom | Consulting complete in Dec, work to commence in 2022 | 10703.93 |  | Kerrsten Norwood | Nicole
67 | Stoneridge Manor - Q2/Q4 - IPAC Capital Fund | N/A - IPAC | 5237 |  | Kerrsten Norwood | Nicole
43 | The Westwood - 2021 - Care Floor Renovation | Consulting complete in Dec, work to commence in 2022 | 43640.6 |  | Kerrsten Norwood | Nicole
44 | The Westwood - 2021 - Keypads/Wander guard | Not complete as of Dec 2021 | 15521.29 |  | Kerrsten Norwood | Nicole
47 | Valley Stream - 2021 - Care Floor Renovation | Consulting complete in Dec, work to commence in 2022 | 9435.5 |  | Kerrsten Norwood | Nicole
71 | Westwood - 2021 - B1 & B2 Fire & Life Safety Compliance | Consulting complete in Dec, work to commence in 2022 | 6596.39 |  | Kerrsten Norwood | Nicole